## KPI Summary
value
report_date | 2026-08-25
avg_sprint_completion_rate_pct | 85.9
avg_bug_reopen_rate_pct | 18.1
avg_pr_review_hours | 16.2
avg_change_failure_rate_pct | 6.9
avg_project_health_score | 88.9
at_risk_project_count | 3
total_projects | 12

## At-Risk Projects
project_id | delivery_risk | quality_risk | review_bottleneck_risk | workload_risk | release_risk_score | project_name | criticality | risk_tier
P009 | 100 | 95.3 | 69.5 | 100 | 91.2 | Fraud-Detection | High | High Risk
P008 | 93.1 | 70 | 89.1 | 97.1 | 87.3 | Data-Pipeline | Medium | High Risk
P011 | 96.6 | 54.2 | 66.1 | 81.4 | 74.6 | Inventory-Service | Medium | High Risk
P004 | 4 | 100 | 30 | 60.6 | 48.6 | Auth-Gateway | Medium | Medium Risk
P005 | 35.8 | 29.4 | 46.7 | 68.5 | 45.1 | Mobile-App-iOS | Low | Medium Risk

## Bottlenecks
team_name | avg_pr_review_hours | bug_reopen_rate_pct | change_failure_rate_pct
Platform-Infra | 23.8773 | 20.1342 | 15.3846
Notifications | 18.432 | 17.7215 | 6.7797
Identity | 14.1168 | 14.3369 | 6.6372
Mobile | 14.0504 | 17.2932 | 4.955
Data-Platform | 13.6041 | 20.5128 | 3.0303

## Quality Issues
project_name | criticality | quality_score
Data-Pipeline | Medium | 85.3211
Auth-Gateway | Medium | 88.2353
Inventory-Service | Medium | 89.7727
Fraud-Detection | High | 90.099
Checkout-Web | Low | 90.8046

## Recommendations
project_name | risk_score | primary_drivers | recommended_action
Fraud-Detection | 91.2 | sprint completion rate is low; defect/escape rate is elevated; PR review time is a bottleneck; team workload is disproportionately high | Recommend immediate leadership review: reallocate reviewer capacity, triage critical-bug backlog, and reassess sprint scope.
Data-Pipeline | 87.3 | sprint completion rate is low; defect/escape rate is elevated; PR review time is a bottleneck; team workload is disproportionately high | Recommend immediate leadership review: reallocate reviewer capacity, triage critical-bug backlog, and reassess sprint scope.
Inventory-Service | 74.6 | sprint completion rate is low; PR review time is a bottleneck; team workload is disproportionately high | Recommend monitoring closely and addressing the top driver this sprint.

## Top Performers
full_name | team_id | seniority | engineering_productivity_score
Elizabeth Fowler | T005 | Senior | 74.8
Jessica Holmes | T005 | Staff | 74.3
Stephanie Ross | T005 | Junior | 74.2
Monica Herrera | T005 | Senior | 71
Daniel Wagner | T006 | Senior | 70
Anthony Rodriguez | T006 | Junior | 69.9
Eric Carney | T006 | Staff | 69.4
Lisa Jackson | T006 | Junior | 67.1
Brian Ramirez | T005 | Staff | 66.9
Judy Baker | T006 | Junior | 66.2

## Team KPIs (full)
team_id | team_name | avg_sprint_completion_rate | avg_sprint_velocity | sprints_count | avg_cycle_time_days | mttr_hours | bug_reopen_rate_pct | escaped_defect_rate_pct | defect_density_pct | avg_pr_review_hours | pr_merge_rate_pct | change_failure_rate_pct | total_deployments | total_releases | release_success_rate_pct | release_delay_rate_pct | avg_release_delay_days | quality_score | delivery_score | devops_score | team_health_score
T001 | Payments | [16 empty] | 100 |  | 100
T002 | Checkout | [16 empty] | 100 |  | 100
T003 | Search | 0.94545 | 52.7 | 10 | 1.0447 | 24.6507 | 18.8889 | 8.8889 | 32.7273 | 13.2428 | 76.2136 | 4.5455 | 66 | 5 | 80 | 20 | 1.66 | 91.1111 | 94.5452 | 95.4545 | 93.6
T004 | Identity | 0.93841 | 46.9667 | 30 | 1.0546 | 24.8316 | 14.3369 | 5.7348 | 36.8074 | 14.1168 | 73.6264 | 6.6372 | 226 | 15 | 33.3333 | 66.6667 | 1.7733 | 94.2652 | 93.8414 | 93.3628 | 93.8
T005 | Platform-Infra | 0.57649 | 30.7 | 30 | 1.7762 | 48.5131 | 20.1342 | 11.745 | 36.9269 | 23.8773 | 75.4159 | 15.3846 | 130 | 15 | 33.3333 | 66.6667 | 3.1867 | 88.255 | 57.6488 | 84.6154 | 76.5
T006 | Mobile | 0.93152 | 46.8 | 30 | 1.1538 | 28.9991 | 17.2932 | 9.7744 | 33.8422 | 14.0504 | 75 | 4.955 | 222 | 15 | 66.6667 | 26.6667 | 0.59286 | 90.2256 | 93.1519 | 95.045 | 92.7
T007 | Notifications | 0.81859 | 41.8 | 10 | 1.3152 | 28.7536 | 17.7215 | 6.3291 | 36.2385 | 18.432 | 75.1323 | 6.7797 | 59 | 5 | 100 | 0 | 0.04 | 93.6709 | 81.8592 | 93.2203 | 89.4
T008 | Data-Platform | 0.94192 | 44.1 | 10 | 1.0971 | 24.5481 | 20.5128 | 7.6923 | 34.8214 | 13.6041 | 71.4286 | 3.0303 | 66 | 5 | 40 | 60 | 1.1 | 92.3077 | 94.192 | 96.9697 | 94.4

## Project Health (full)
project_id | quality_score | delivery_score | devops_score | project_health_score | project_name | criticality
P009 | 90.099 | 56.2782 | 79.5455 | 75.1 | Fraud-Detection | High
P008 | 85.3211 | 59.0385 | 87.1795 | 76.7 | Data-Pipeline | Medium
P011 | 89.7727 | 57.6297 | 87.234 | 77.8 | Inventory-Service | Medium
P005 | 93.6709 | 81.8592 | 93.2203 | 89.4 | Mobile-App-iOS | Low
P004 | 88.2353 | 94.5199 | 92.4051 | 91.7 | Auth-Gateway | Medium
P012 | 91.4894 | 88.8315 | 97.0588 | 92.2 | Analytics-Dashboard | Low
P007 | 91.358 | 93.5388 | 94.0299 | 92.9 | Notification-Hub | Medium
P002 | 91.1111 | 94.5452 | 95.4545 | 93.6 | Payments-API | Medium
P003 | 95.283 | 92.7622 | 93.1034 | 93.7 | Search-Service | Medium
P001 | 90.8046 | 96.1042 | 96 | 94.2 | Checkout-Web | Low
P010 | 92.3077 | 94.192 | 96.9697 | 94.4 | Customer-Portal | High
P006 | 95.6522 | 95.2231 | 93.0556 | 94.7 | Mobile-App-Android | Low